## sprint backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | 1 | Planning & Analysis: Define system requirements, verification flow, dataset classes, and security objectives. | 2025-12-05 | 2025-12-10 | Everyone | Study Aadhaar document structure, define verification levels, finalize dataset classes, and select appropriate technologies. | done | 8hrs | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2
SPRINT 2
2 | 2 | Dataset Collection & Preparation | 2025-12-11 | 2025-12-15 | Ganthimathi | Collect real, fake, and non-Aadhaar images, label them correctly, resize, normalize, and split into train/validation/test sets. | done | 10hrs | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2
SPRINT 3
3 | 3 | Model Training (YOLO Classification) | 2025-12-15 | 2025-12-17 | Ganthimathi | rule based validation to compare Aadhar QR data and OCR extracted fields | done | 7hrs | Day 1: 2; Day 2: 3; Day 3: 2
SPRINT 4
4 | 4 | OCR Text Extraction | 2025-12-15 | 2025-12-16 | Ganthimathi | Configure Tesseract OCR, preprocess images, extract text, and parse Aadhaar-specific fields such as name, DOB, and gender. | done | 5hrs | Day 1: 2.5; Day 2: 2.5
SPRINT 5
5 | 5 | QR Code Detection & Validation | 2025-12-27 | 2025-12-27 | Ganthimathi | Detect QR codes using OpenCV and PyZbar, identify encrypted Aadhaar QR, and validate authenticity signals. | done | 3
SPRINT 6
6 | 6 | Multi-Level Decision Engine | 2025-12-17 | 2025-12-18 | Ganthimathi | Combine YOLO classification, OCR results, and QR verification using rule-based logic to produce a final verdict. | done | 12 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2; Day 6: 2
SPRINT 7
7 | 7 | Backend Development | 2026-01-01 | 2026-01-02 | Ganthimathi | Develop Flask APIs to handle image uploads, execute the verification pipeline, and return structured JSON responses. | done | 8hrs | Day 1: 4; Day 2: 4
SPRINT 8
8 | 8 | Frontend Development | 2025-12-27 | 2026-01-03 | Ganthimathi | Implement user login, access control, verification history tracking, and secure data handling mechanisms. | done | 25hrs | Day 1: 4; Day 2: 5; Day 3: 4; Day 4: 3; Day 5: 3; Day 6: 3; Day 7: 2; Day 8: 2
Note on D1: ====== ID#AAABySIrxJc Please enter the dates in either of these formats (2026-01-06 15:39:39) 9/15/2016 or 15-Sep-2016
Note on E1: ====== ID#AAABySIrxIw Please enter the dates in either of these formats (2026-01-06 15:39:39) 9/15/2016 or 15-Sep-2016
Note on I2: ====== ID#AAABySdK7Mk Sumeet Kumar Barua08 (2026-01-06 15:39:39) This is the total task estimated in hours for all the user stories
Note on J2: ====== ID#AAABySIrxJY Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 1 work
Note on K2: ====== ID#AAABySIrxI4 Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 2 work
Note on L2: ====== ID#AAABySIrxJA Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 3 work
Note on M2: ====== ID#AAABySIrxIo Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 4 work
Note on N2: ====== ID#AAABySIrxJQ Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 5 work
Note on O2: ====== ID#AAABySIrxJM Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 6 work
Note on P2: ====== ID#AAABySIrxIs Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 7 work
Note on Q2: ====== ID#AAABySIrxI0 Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 8 work
Note on R2: ====== ID#AAABySdK7Mg Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 9 work
Note on S2: ====== ID#AAABySIrxIk Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 10 work
Note on T2: ====== ID#AAABySIrxJE Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 11 work
Note on U2: ====== ID#AAABySIrxI8 Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 12 work
Note on V2: ====== ID#AAABySIrxJI Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 13 work
Note on W2: ====== ID#AAABySIrxJU Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 14 work

## standup meetings
Sprint | Day | Impediments | Action Taken
1 | 2025-12-09 | Unable to obtain fake Aadhaar data | Generated synthetic and simulated fake Aadhaar samples
2 | 2025-12-14 | Difficulty in accurate OCR text extraction | extraction Integrated PaddleOCR for improved text recognition accuracy
3
4
5
6
7
8

## retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-12-05 | 2025-12-10 | Ganthimathi | Kaggle Data search
2 | 2 | 2025-12-11 | 2025-12-15 | Ganthimathi | OCR Processing
3 | 3
4 | 4
5 | 5
6 | 6
7 | 7
8 | 8

## product backlog
Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 |  | Collected Aadhaar and other KYC document images and prepared datasets for OCR, CNN, and ML models. Performed image preprocessing, normalization, QR extraction readiness, and metadata preparation for downstream validation. |  | used google, kaggle,fake images generated for dataset, and preprocessing done using python libraries | everyone
2 |  | Implemented PaddleOCR to extract structured text fields from Aadhaar documents and generated standardized JSON outputs. Built OCR post-processing logic to clean text, validate formats, and prepare extracted data for rule-based and ML validation. |  | according to goverment rules validation done and ocr extraction techinques used | Ganthimathi
3 |  | Extracted Aadhaar QR code data and compared it against OCR-extracted fields using rule-based validation. Generated consistency scores and flags to detect mismatches between QR data, OCR text, and document structure. |  | qr decoder used | Ganthimathi
4 |  | Developed a CNN model to classify documents as real Aadhaar, fake Aadhaar, or non-Aadhaar images. Integrated image forensics features to detect tampering indicators such as overlays, font inconsistencies, and artifacts. |  | predefined cnn model used | Ganthimathi
5 |  | Performed face extraction from Aadhaar photo and live/person image for comparison. Applied face-matching logic to verify identity consistency when the document is classified as a real Aadhaar. |  | predefined model used | Ganthimathi
6 |  | Designed an ML model that takes OCR data, QR validation results, and image forensics inputs. The model produces a final Real/Fake classification with confidence-based fraud risk assessment. |  | coustmize model made | Ganthimathi
7 |  | Integrated OCR, CNN, QR validation, face matching, and ML models into a single end-to-end pipeline. Ensured smooth data flow between modules and real-time decision output in JSON format. |  | all parts were integrated | Ganthimathi
8 |  | Tested the complete pipeline with multiple Aadhaar scenarios including genuine, tampered, and fake samples. Validated system accuracy, reduced false positives, and ensured readiness for cloud-based deployment. and ui part made |  | Postman for API testing, HTML, CSS, JS for Frontend | Ganthimathi
Note on E1: ====== ID#AAABySIrxIg Sumeet Kumar Barua08 (2026-01-06 15:39:39) Mention the US ID(s) on which the user story depends.